## Timeline
IT 691 CAPSTONE PROJECT TIMELINE Pace University Professor
Phase | Key activities | Start | Finish | Deliverable | Owner / lead | Status | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13
[7 empty] | 2026-09-22 | 2026-09-29 | 2026-10-06 | 2026-10-13 | 2026-10-20 | 2026-10-27 | 2026-11-03 | 2026-11-10 | 2026-11-17 | 2026-11-24 | 2026-12-01
Initiation & planning | Scope, roles, agreement | 2026-09-20 | 2026-09-26 | Powerpoint with decisions | Nira | Complete | bar: 2026-09-22
Define working agreements | Working agreements and project scope | 2026-09-18 | 2026-09-25 | Powerpoint with decisions | Team | bar: 2026-09-22
Refined Research question | Revise research problem and question | 2026-09-21 | 2026-09-25 |  | Team | Complete | bar: 2026-09-22
Research | Literature review and data preparation | 2026-09-27 | 2026-10-10 | Research summary and prepared dataset |  | In progress | bar: 2026-09-22 to 2026-12-01
Dataset | Research and finalize decision | 2026-09-13 | 2026-09-24 | Add dataset decisions to powerpoint |  | Complete
Tools | Review tool options and decision | 2026-09-22 | 2026-10-02 | Add tools to powerpoint |  | In progress
Building Model |  |  |  |  | Jenn/Paul
Scripting phase 1 | Begin scripting | 2026-10-02 | 2026-10-06
Setup jupyter notebook
Dataset: Clean and harmonize | Using pandas, remove dataset columns, clean and harmonize | 2026-10-01 | 2026-10-05 | Clean model ready dataset | Nira/Kevin | Not started
Create model label |  |  |  |  | Jenn/Paul | Not started
Separate features | separate features from target and creating training and test sets |  |  |  | Jenn/Paul | Not started
Process data | using scikit learn |  |  |  | Jenn/Paul | Not started
Build decision tree | [5 empty] | Not started
Build random forest | [5 empty] | Not started
Progress Report 1 | [5 empty] | Not started
Draft |  | 2026-10-02 | 2026-10-06 |  | Nira | Not started
Final version |  | 2026-10-07 | 2026-10-11 | Submit final in brightspace | Nira | Not started
Traditional baseline | Rules and thresholds | 2026-10-11 | 2026-10-24 | Working baseline and results | TBD | Not started | bar: 2026-10-06 to 2026-10-13
AI model development | Train and test model | 2026-10-25 | 2026-11-07 | Working AI prototype | TBD | Not started | bar: 2026-09-22 to 2026-12-01
Combined detection | Compare and integrate approaches | 2026-11-08 | 2026-11-14 | Combined detection results | TBD | Not started | bar: 2026-11-03 to 2026-11-10
Validation | Metrics and error analysis | 2026-11-15 | 2026-11-21 | Performance comparison | TBD | Not started | bar: 2026-09-22 to 2026-12-01
Report & presentation | Documentation, GitHub, slides | 2026-11-22 | 2026-11-28 | Final report and presentation | TBD | Not started | bar: 2026-10-06 to 2026-11-24
Review & submission | QA and final delivery | 2026-11-29 | 2026-12-01 12:00 | Completed capstone submission | TBD | Not started | bar: 2026-09-22 to 2026-12-01

## Decision Log
Task | Decision | Date | Notes
Tools | Powerpoint, Excel, Suricata, Skikit-learn (decision tree and random forest models), Pandas, Github
Programming | Python scripts
Datasets | WUSTL-IIoT-2021, UNSW-NB15, and CIC-IDS2017 (2 training, 1 testing) | 2026-09-25

## Task Tracker
Phase | Task / deliverable | Owner | Start date | Due date | Status | % complete | Dependency | Risk / blocker | Notes
Initiation & planning | Project plan and working agreement | TBD | 2026-09-20 | 2026-09-26 | Not started | 0 | None
Research & dataset | Research summary and prepared dataset | TBD | 2026-09-27 | 2026-10-10 | Not started | 0 | Initiation & planning
Traditional baseline | Working baseline and results | TBD | 2026-10-11 | 2026-10-24 | Not started | 0 | Research & dataset
AI model development | Working AI prototype | TBD | 2026-10-25 | 2026-11-07 | Not started | 0 | Traditional baseline
Combined detection | Combined detection results | TBD | 2026-11-08 | 2026-11-14 | Not started | 0 | AI model development
Validation | Performance comparison | TBD | 2026-11-15 | 2026-11-21 | Not started | 0 | Combined detection
Report & presentation | Final report and presentation | TBD | 2026-11-22 | 2026-11-28 | Not started | 0 | Validation
Review & submission | Completed capstone submission | TBD | 2026-11-29 | 2026-12-01 12:00 | Not started | 0 | Report & presentation